| 1. This table is designed to show the dependencies between progress on all of the Components listed in the Guidance. The Components are clustered as in the graphic at page 4 of the Strategic Planning Action Guide in the Guidance. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2. Specifically for each Component, it lists any components for which significant deployment must have been completed in order for deployment of the follow-up Component to be practicable. |  |  |  |  |  |  |  |  |
| 3. Similarly, for each Component it lists all Components for which deployment is made possible by the prior Component. |  |  |  |  |  |  |  |  |
| 4. An additional column identifies the step(s) that are so critical to the deployment, and so likely to interfere with it if not in place, that immediate work on the step is recommended, even prior to the commencement of the planning process itself. (Do It Yesterday!) |  |  |  |  |  |  |  |  |
| Component | Dependant Upon | Others Depending On | Critical Prior Step | Notes |  |  |  |  |
|  |  |  | (Do It Yesterday!) |  |  |  |  |  |
| 1. Foundational Capacity |  |  |  |  |  |  |  |  |
| Design, Governance & Management | None. | All. | Acceptance by stakeholders of decision-making process and authority. | Different components depend on different levels of completion of this component. |  |  |  |  |
| Resource Planning | Design, Governance, etc. | Higher resource needing components (more expensive). | Agreement of shared responsibility and allocation of resources. | Important that process includes reprogramming options and non-resource contingencies. |  |  |  |  |
| Triage, Referral, & Channel Integration | None to begin | All Expansion Services. | Agreement on general methodology. |  |  |  |  |  |
| Technology Capacity | None | Many can start without this, but will be much better with this vision integrated. | Appointment of State ATJ Technology Director. | Could be on assignment from stakeholder. |  |  |  |  |
| Judicial Education Programs | None | All require some of this component in place. | Assignment of responsibility. | Judicial leadership branch needed earlier than courtroom techniques. |  |  |  |  |
| Community Integration & Prevention | None. | None. | Community Network Recruitment, particularly into design, governance and management. | While not formally required for design, governance and management, critical for success. |  |  |  |  |

| Component | Dependant Upon | Others Depending On | Critical Prior Step | Notes |
| --- | --- | --- | --- | --- |
|  |  |  | (Do It Yesterday!) |  |
| 2. Foundational Services |  |  |  |  |
| Plain Language Forms | None. | All except Foundational capacity list (except counsel expansion). | Promulgation authority for state standardized forms. (mandated acceptance). | Critical to efficiency in all systems. |
| Broad Self-Help Informational Services | None, but forms critical. | Triage, courtroom assistance, compliance assistance, ADR integration. | Rules/training on appropriate staff role. | Critical to making the system as a whole work. |
| Language Services Integration | Broad Informational Services. | None. | Language Leadership goes beyond interpreters alone. | Rules must address appropriate informational roles for interpreters at least when others not available. |

| Component | Dependant Upon | Others Depending On | Critical Prior Step | Notes |
| --- | --- | --- | --- | --- |
|  |  |  | (Do It Yesterday!) |  |
| 3. Expansion Services |  |  |  |  |
| Expansion and Efficiency Improvements of Full Service Representation | Design, Governance and Management, Triage, Resource Planning. | None. | Funding collaborations firm. | Triage makes the case best. |
| Unbundled (Discrete Task) Legal Assistance | None. | None. | Rules governing unbundling. | Marketing relationships critical. |
| Courtroom Assistance Services | Forms, Informational Services. | None. | Rules governing staff roles. |  |
| Compliance Assistance | Informational services. | None. | Understanding neutrality of compliance assistance. | Perhaps most neglected component in whole system. |
| Alternative Dispute Resolution Integration | Triage. | None. | Rules requiring appropriate informational assistance in ADR process itself. | The JFA component here is Integration not the actual services. This is going to be an extremely sensitive process politically. |

| Component | Dependant Upon | Others Depending On | Critical Prior Step | Notes |
| --- | --- | --- | --- | --- |
|  |  |  | (Do It Yesterday!) |  |
| 4. System Completion |  |  |  |  |
| Simplification | None, although this made easier by each of, and all the prior components. | None, although a simpler system will make every one of the components easier to deploy and increase their cost effectiveness. | Stakeholder commitment. | Could be done first in one court/case type. |
| Non-Lawyer Role Flexibility | Forms, judicial education. | None. | Understanding actual current rules; judicial leadership buy-in and support. | Current law is often far more flexible than is realized. |